## Overall Scope for March
Initiative | Category | Status | Milestone | Priority | Issue # | Target Date | Testing % (estimate) | Owner | Notes
In Prod — Question Types
Multiple Choice | Question Type | In Prod | Pre-Launch (In Prod) | N/A |  | Mar 10, 2026 | 80%
Rating | Question Type | In Prod | Pre-Launch (In Prod) | N/A |  | Mar 10, 2026 | 80%
Open End | Question Type | In Prod | Pre-Launch (In Prod) | N/A |  | Mar 10, 2026 | 60%
Scale | Question Type | In Prod | Pre-Launch (In Prod) | N/A |  | Mar 10, 2026 | 60%
Rank | Question Type | In Prod | Pre-Launch (In Prod) | N/A |  | Mar 10, 2026 | 60%
NPS | Question Type | In Prod | Pre-Launch (In Prod) | N/A |  | Mar 10, 2026 | 80%
Custom Grid | Question Type | In Prod | Pre-Launch (In Prod) | N/A |  | Mar 10, 2026 | 30%
In Prod — Survey Builder & Setup
Project & Survey Setup | Platform / Workflow | In Prod | Pre-Launch (In Prod) | N/A |  | Mar 10, 2026 | 90%
Version History | Platform / Workflow | In Prod | Pre-Launch (In Prod) | N/A |  | Mar 10, 2026 | 40%
AI Survey Generation | AI Feature | In Prod | Pre-Launch (In Prod) | N/A |  | Mar 10, 2026 | 40%
Question Text Piping | Survey Feature | In Prod | Pre-Launch (In Prod) | N/A |  | Mar 10, 2026 | 20%
Screener Questions | Survey Feature | In Prod | Pre-Launch (In Prod) | N/A |  | Mar 10, 2026 | 90%
Screener Qualification Logic | Survey Feature | In Prod | Pre-Launch (In Prod) | N/A |  | Mar 10, 2026 | 70%
In-Step Targeting | Survey Feature | In Prod | Pre-Launch (In Prod) | N/A |  | Mar 10, 2026 | 50%
Quotas | Survey Feature | In Prod | Pre-Launch (In Prod) | N/A |  | Mar 10, 2026 | 50%
Audience & Targeting | Survey Feature | In Prod | Pre-Launch (In Prod) | N/A |  | Mar 10, 2026 | 50%
Monadic Survey Type | Survey Type | In Prod | Pre-Launch (In Prod) | N/A |  | Mar 10, 2026 | 40%
Media / Image on Questions | Survey Feature | In Prod | Pre-Launch (In Prod) | N/A |  | Mar 10, 2026 | 50%
Bulk Paste for Answer Options | Survey Feature | In Prod | Pre-Launch (In Prod) | N/A |  | Mar 10, 2026 | 90%
Review & Launch | Platform / Workflow | In Prod | Pre-Launch (In Prod) | N/A |  | Mar 10, 2026 | 90%
Survey Pause / Resume / Close | Platform / Workflow | In Prod | Pre-Launch (In Prod) | N/A |  | Mar 10, 2026 | 60% |  | User clicks launch --> Survey actually does not get launched. It goes to PureSpectrum as a draft, Steve's team is notified, they review and then launch. Until it's actually set to "LIVE" on PureSpectrum's side, the user currently cannot pause or close the survey. We have a popup notifying them of this. It's a non-ideal workaround we needed to add before customers got early access to platform.
In Prod — Results & Analysis
Results Dashboard | Results & Analysis | In Prod | Pre-Launch (In Prod) | N/A |  | Mar 10, 2026 | 60%
AI Survey Summaries | AI Feature | In Prod | Pre-Launch (In Prod) | N/A |  | Mar 10, 2026 | 30%
Raw Data Export | Results & Analysis | In Prod | Pre-Launch (In Prod) | N/A |  | Mar 10, 2026 | 80%
Quota Progress in Results | Results & Analysis | In Prod | Pre-Launch (In Prod) | N/A |  | Mar 10, 2026 | 50%
In Prod — Project-Level Features
Research Planner / Research Brief | AI Feature | In Prod | Pre-Launch (In Prod) | N/A |  | Mar 10, 2026 | 50% |  | Brock, Riche, and I were in early discussions to re-think a lot of this… but just never got around to truly planning it out
Project Collaboration Hub | Collaboration | In Prod | Pre-Launch (In Prod) | N/A |  | Mar 10, 2026 | 20% |  | Brock, Riche, and I were in early discussions to re-think a lot of this… but just never got around to truly planning it out
Insights Tab | Collaboration | In Prod | Pre-Launch (In Prod) | N/A |  | Mar 10, 2026 | 20% |  | Brock, Riche, and I were in early discussions to re-think a lot of this… but just never got around to truly planning it out
AI Chat Threads | AI Feature | In Prod | Pre-Launch (In Prod) | N/A |  | Mar 10, 2026 | 20% |  | Brock, Riche, and I were in early discussions to re-think a lot of this… but just never got around to truly planning it out
Files Tab | Collaboration | In Prod | Pre-Launch (In Prod) | N/A |  | Mar 10, 2026 | 20%
Legacy Survey Surface | Platform / Workflow | In Prod | Pre-Launch (In Prod) | N/A |  | Mar 10, 2026 | 0%
In Prod — Platform Integration
PureSpectrum Integration | Integration | In Prod | Pre-Launch (In Prod) | N/A |  | Mar 10, 2026 | 90%
Credit System | Platform / Workflow | In Prod | Pre-Launch (In Prod) | N/A |  | Mar 10, 2026 | 90%
Feature Flags (Flipt) | Platform / Workflow | In Prod | Pre-Launch (In Prod) | N/A |  | Mar 10, 2026 | 60%
Verisoul Respondent Quality | Integration | In Prod | Pre-Launch (In Prod) | N/A | #774 | Mar 10, 2026 | 80%
IN QA / IN PROGRESS / OR BEHIND FEATURE FLAG
TURF Question Type | Question Type | Feature Flag | Apr 1 Launch | High | #245 | 2026-03-20 | 0%
Images-as-Answer Choices | Question Type | In QA | Apr 1 Launch | High | #784 | 2026-03-13 | 0%
Sequential Monadic | Survey Type | Feature Flag | Q2 2026 | N/A |  | TBD - Needs testing | 0%
Auto-Assign* | Platform / Workflow | In QA, debugging | Apr 1 Launch | High | #244 | 2026-03-20 | 0% |  | This is in QA. Anton is indentifying and correcting bugs, but this will need to be ironed out before we can get to piping answer options
TO BE PICKED UP WEEK OF 3/16
MaxDiff | Question Type | Start 3/16 | Apr 1 Launch | High | #243 | 2026-03-20 | 0% | Nicole
Monadic Results / Significance Testing | Platform / Workflow | Start 3/16 | Apr 1 Launch | High | #790 | 2026-03-20 | 0% | Not yet assigned
Data Explorer 2.0 | AI Feature | Start 3/16 | Apr 1 Launch | High | #147 | 2026-03-20 | 0% | George
Enhanced AI Summarization | AI Feature | Start 3/16 | Apr 1 Launch | High | To be scoped, Bryan and I both have some doc on this | 2026-03-20 | 0% | Impact Pod
Respondent UI/UX Overhaul* | Platform / Workflow | Start 3/17 | Apr 1 Launch | High | #829 | 2026-03-20 | 0% | Erman and Ali? | Can we just "copy and paste" this? Probably more complex to do that… since we need to map all of the question types and configurations to however they're defined on v2
Piping-in-Answer-Options* | Survey Feature | Start 3/18 | Apr 1 Launch | High | #247 | 2026-03-20 | 0% | Nicole | This is quite complex and might be blocked until Auto-Assign is figured out
AI Survey Copilot | AI Feature | Start 3/18 | Apr 1 Launch | High | #149 | 2026-03-20 | 0% | Not yet assigned | Leverage prompts from "Research Buddy" -- helps guide the user
SuSp Workstream 1: Survey Setup and Builder | Platform / Workflow | In Progress | Apr 1 Launch | High | #249 | 2026-03-13 | 0% | Bala
SuSp Workstream 2: Launch & Integration | Platform / Workflow | Start 3/16 | Apr 1 Launch | High | #249 | 2026-03-18 | 0% | Bala (Haseeb to help?)
SuSp Workstream 3: Fielding & Monitoring | Platform / Workflow | Start 3/18 | Apr 1 Launch | High | #249 | 2026-03-20 | 0% | Bala (Haseeb to help?)
TO BE PICKED UP WEEK OF 3/23
SuSp Workstream 4: Post-Interview & Analysis | Platform / Workflow | Start 3/16 | Apr 1 Launch | High | #249 | 2026-03-25 | 0% | Not yet assigned | Analysis is in still in a separate repo and needs to be refactored. I can probably at least start this on Friday 3/20
New Pricing Implementation | Platform / Workflow | Start 3/23 | Apr 1 Launch | High |  | 2026-03-27 | 0% | Tom / Max/ Steve | Wait n Save / Express / etc.
Feasibility Estimator (necessary for new pricing implementation) | AI Feature | Start 3/23 | Apr 1 Launch | High |  | 2026-03-27 | 0% | Steve / Max | Steve has a prototype for this
Prompting - Research Scoping | Polish | Start 3/23 | Apr 1 Launch | High |  | 2026-03-27 | 0% |  | Adapt all of the prompts that already exist in Research Buddy
Prompting - AI Summarization | Polish | Start 3/23 | Apr 1 Launch | High |  | 2026-03-27 | 0% |  | Adapt all of the prompts that already exist in Research Buddy
Prompting - Questionnaire Design (Suzy Speaks) | Polish | Start 3/23 | Apr 1 Launch | High |  | 2026-03-27 | 0% |  | Adapt all of the prompts that already exist in Research Buddy
Prompting - Questionnaire Design (Quant) | Polish | Start 3/23 | Apr 1 Launch | High |  | 2026-03-27 | 0% |  | Adapt all of the prompts that already exist in Research Buddy
TESTING AND BUG FIXES! | Platform / Workflow | Ongoing | Apr 1 Launch | High |  | 2026-03-27 | 0%
WRAP UP SUZY SPEAKS! | Platform / Workflow | Ongoing | Apr 1 Launch | High |  | 2026-03-27 | 0%
WHAT WILL BE LIKELY MISSING ON 4/1
Chart-Level Exports and Downloads | v2 Feature
Question-Level Insights Page (e.g., crosstabs) | v2 Feature
Excel Tables | v2 Feature | Might come with Data Explorer 2.0
Biotic 2.0 | v2 Feature | Brit has a prototype of this
Suzy Live | v2 Feature | Brit has a prototype of this
Suzy Connect | v2 Feature
Global | v2 Feature
Video Open Ends | v2 Feature | May be skipped altogether or just merged into Suzy Speaks | [6 empty] | "Express Suzy Speaks"
Question & Survey Templates | v2 Feature | [7 empty] | Easiest path here is to just give an example library to AI survey copilot
ADDITIONAL PLANNED FEATURES — Q2 2026 (Apr 1 - Jun 30)
FieldOps Agent | AI Feature | Planned | Q2 2026 |  | #230 | Jun 30, 2026 | 0%
Conjoint Analysis | Question Type | Planned | Q2 2026 |  | #230 | Jun 30, 2026 | 0% |  | Choice-based conjoint question type
VanWestendorp | Question Type | Planned | Q2 2026 |  | #248 | Jun 30, 2026 | 0% |  | Price sensitivity question type
Sequential Monadic - GA | Survey Type | Planned | Q2 2026 |  |  | Jun 30, 2026 | 0% |  | Remove feature flag; general availability
Global | Integration | Planned | Q2 2026 |  | #833 | Jun 30, 2026 | 0% |  | George already has a ticket for this… unsure of progress
Audio Open Ends | Integration | Planned | Q2 2026 |  | #787 | Jun 30, 2026 | 0% |  | Needs further validation
Block Randomization | Integration | Planned | Q2 2026 |  | #779 | Jun 30, 2026 | 0% |  | Important for features like sequential monadic
Colour | Status | Description
Green | In Production | Already shipped (Feb 9 - Mar 10, 2026)
Yellow | In Progress | Targeting Apr 1 launch
Red | Not in Scope for April 1st | v2 features that will be missing from the new platform
Blue | Planned | Q2 2026 roadmap items

## Suzy Speaks — Apr 1 Scope
Suzy Speaks — April 1, 2026 Launch Scope
IN SCOPE — April 1, 2026
Feature / Capability | Description | Notes
End-to-End Study Builder | A complete creation flow — Setup, Audience, Discussion Guide, and Review & Launch — built on the existing survey builder shell. The StudyType discriminator (Survey vs. Speaks) gates the correct UI, panels, and launch target throughout the experience. Goal of also getting AI Survey Builder Copilot operational to build ontop of this UI/UX as well
Study Setup & Configuration | Study name, internal description, research type category, respondent-facing title, background objectives, research hypotheses, study size (target N), and expected interview duration. All fields feed AI moderator context and the analysis dashboard.
Audience Targeting | Full demographic targeting: gender, age range, household income, ethnicity, Hispanic origin, relationship status, parenting status, household size, state (all 50), region (4), education, employment status, and device type. Same targeting capabilities as the survey product. | Powered by Prodege panel. Targeting parameters passed to Prodege API at launch.
Quotas | Profile-field quotas (gender, age, ethnicity, HHI, etc.) with target percentages, flex tolerances, random or least-fill fill strategies, and per-quota pause/enable controls. Max-response cap enforced across the study. | Same quota engine as surveys; no screener-question quotas in Speaks v1.
Auto-Send (Native Launch) | Study launch wired directly to the Prodege Research Management API. Respondent invitations sent automatically. Signed entry URLs generated per respondent. Webhook callbacks handle complete / terminate / overquota events natively.
Screener Logic | A dedicated screener section before the live interview. Supports multiple choice and other quant question types. Per-answer Qualify / Terminate actions. Multi-group OR/AND qualification logic with selected/did-not-select conditions and any-of/all-of/none-of match operators. | Quant question types (MC, Rating, etc.) ARE supported here — only restricted from the discussion guide itself.
Discussion Guide | Structured guide with named sections, primary questions, probing follow-ups, and per-question depth hints. The AI moderator follows the guide during the live interview, probing naturally within each topic before advancing. Guide is plaintext / qualitative only. | No quant question types in the guide. Probing levels and follow-ups can be configured
AI-Moderated Live Interviews | Respondents join a live voice interview conducted by an AI moderator powered by OpenAI Realtime API and GetStream. The moderator runs the screening flow, qualifies or terminates, then conducts the full discussion guide interview. Transcripts and recordings are stored on completion. | Audio-only for v1
Analysis Dashboard | A rich post-study results experience including: • Results and themes cut by key audience segments • AI-generated summaries and charts by research objective • AI-generated summaries and charts by hypothesis • Per-question summaries with supporting evidence • Full "quant out of qual" experience, with all questions coded and each quantified theme mapped back to actual transcript responses with highlighted relevant snippets • Scrollable, structured layout across all completed interviews | Analysis triggered automatically when the study is marked Complete (all interviews finished).
Exports | Two export types available from the analysis dashboard: 1. Raw data with full transcripts, metadata, and AI classifications 2. Gemini-generated infographic — a visual one-pager summarising study findings. 3. [Stretch] Stories deck | Infographic powered by Gemini. AI classifications use the same pipeline as analysis summaries.
OUT OF SCOPE — April 1, 2026
Feature / Capability | Description | Notes
Media Attachments | [Primary stretch goal] Researchers cannot attach images, video clips, or files to discussion guide questions as stimulus material. The interview is audio and text only — no visual assets shown to respondents. | No image/video stimulus during the live interview. May be revisited post-launch.
Monadic / Concept Testing | No concept rotation or per-respondent concept assignment in Speaks v1. Each respondent experiences a single, uniform discussion guide — there is no stimulus splitting or per-concept results breakdown. | Monadic is a Q2+ consideration once the core qualitative workflow (and media attachments) are stable
UI/UX Testing | No screen share, prototype walkthroughs, clickstream capture, or task-based usability testing modality. Speaks v1 is a pure conversational interview product. | UX research modality requires separate tooling and respondent technical setup — out of scope for v1.
Video Mode | Interviews are audio-only. There is no video capture, respondent camera feed, or video playback in the analysis dashboard. Video recordings are not stored.
Global | US-only audience via Prodege panel in v1. No multi-language support, no international panel access, no locale-specific compliance handling. | English-language, US-based respondents only at launch. International is a future milestone.
Quant Questions in Discussion Guide | Multiple choice, rating, scale, NPS, rank, and other quantitative question types are not available within the live discussion guide. The AI moderator is designed for open-ended qualitative conversation only. | Quant questions ARE fully supported in the screener section — only restricted from the guide itself.